## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Fundamentals and Prequsites to work with Project
|  | 2 | Understanding the Project, Project environment setup and Database integration
|  | 3 | Parallel Text Handling
|  | 4 | Paralelle text Loading, Breaking, Grouping, Searching & Integration
Note on F1: ====== ID#AAABs5CmnRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
w
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Fundamentals and Prequsites to work work with Project | 18-09-2025 | 2nd Oct | Ayush Kumar | Basics of python alongwith oops and function paradigm | Done |  | Introduciton |  |  | Setup | keywords and naming conventions | Functions and keywords | Flow control and loops |  | Strings and errors | mutable and ommutable data types | object oriented approach | functions part 2 and some programs | python packages and modules | oops paradigm
2 |  | Understanding the Project, Project environment setup and Database integration | 3rd Oct | 17th Oct | Ayush Kumar | Learning Multi-Processing and Project Understanding | Done |  | OOPS |  |  | Packages | Fundamentals of multi-processing | Discussion upon multi-processing and pipes | revised python concepts | Project briefing | Interactive Session | setting up the environment | session on SQLite | interactive session - 2 | Multi-tasking in python | examples on multi-tasking
3 |  | Text handling | 18th Oct | 1st Nov | Ayush Kumar | practicing workflows and establishing the core project setup | Done |  |  | code practice | notes walkthrough | Multi-tasking with python | Thread Pool Executer | Went through running notes | Session on regular expressions | practiced multi tasking | Practiced Thread pool executor | Pattern Matching and done some examples |  | Understanding the flow of execution | Rule based tagging | Execution of code
4 |  | Paralelle text Loading, Breaking and Grouping | 2nd Nov | 16th Nov | Ayush Kumar |  | Done |  |  | Hands-on implementation | Text Breaking and Grouping | Done some examples | Grouping and text breaking | Code walkthrough | practiced | Grouping and Text breaking | performance optimization | Code implementation | doubt clearing session | SMTP | Practiced code | Notes revision
Note on D2: ====== ID#AAABs5CmnRY Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABs5CmnQ4 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABs5CmnRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABs5CmnQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABs5CmnQg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABs5CmnQk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABs5CmnRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABs5CmnRU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABs5CmnRI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABs5CmnQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABs5CmnQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABs5CmnQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABs5CmnRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABs5CmnRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABs5CmnQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABs5CmnRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABs5CmnRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Confusion regarding Python Environment variables and Path setup. | Re-installed Anaconda and configured system path manually.
Sprint 1 | Day 8 | Difficulty understanding __init__ vs normal methods in OOP. | Reviewed documentation and practiced Class examples with mentor.
Sprint 1 | Day 14 | Database 'Locked' error when running multiple scripts on SQLite. | Implemented logic to close cursors/connections properly after execution.
Sprint 1 | Day 20 | Multiprocessing not behaving as expected (Global Interpreter Lock). | Switched to learning ThreadPoolExecutor for I/O bound tasks.
Sprint 1 | Day 32 | Regex patterns failing to capture specific email formats in text. | Used regex101.com to debug and refine the pattern matching logic.
Sprint 1 | Day 45 | Performance lag when loading large text files for breaking. | Optimized code by implementing chunk-based file reading.
Sprint 1 | Day 55 | SMTP server connection timing out during testing. | Checked firewall settings and corrected the port number in code.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 (Phase 1) | 2025-09-18 | 2025-10-02 | Ayush Kumar | focusing on naming conventions from the start. | Writing code without comments. | Practicing small OOP programs daily. | Created a 'Best Practices' checklist for code writing.
2 | Sprint 1 (Phase 2) | 2025-10-03 | 2025-10-17 | Ayush Kumar | Using virtual environments for different library versions. | Ignoring Exception Handling in Database connections. | Interactive sessions for logic building. | Implemented Try-Except blocks in all DB modules.
3 | Sprint 1 (Phase 3) | 2025-10-18 | 2025-11-01 | Ayush Kumar | Visualizing the thread flow before coding. | Writing complex Regular Expressions in a single line. | Using ThreadPoolExecutor for parallel tasks. | Broke down complex Regex patterns into variables for readability.
4 | Sprint 1 (Phase 4) | 2025-11-02 | 2025-11-16 | Ayush Kumar | Performance testing on larger datasets earlier. | Hardcoding file paths in the main script. | Code optimization and modularization. | Refactored the text loading module to be dynamic.